FLOWFORGE

Workflow Management Platform

AI Agent Development Plan

Building FlowForge with Claude & Gemini AI Coding Agents

🤖

Version 1.0 | February 2026

Estimated Duration: 4-6 Months

Human Team: 3-5 Engineers (Oversight & Review)

AI Agents: Claude Code, Gemini Code Assist, GitHub Copilot

# Executive Summary

This implementation plan outlines a radically accelerated approach to building FlowForge using AI coding agents as the primary developers. Instead of a traditional 18-24 month timeline with 25-40 engineers, this plan leverages AI agents like Claude (via Claude Code / Cursor / Aider) and Google Gemini (via Gemini Code Assist) to compress development to 4-6 months with a small human oversight team.

AI coding agents will generate the majority of code, with human engineers focusing on architecture decisions, code review, quality assurance, and areas requiring deep domain expertise. This approach represents a paradigm shift in software development.

## Traditional vs AI Agent Development

| Aspect | Traditional Approach | AI Agent Approach |
| --- | --- | --- |
| Timeline | 18-24 months | 4-6 months |
| Team Size | 25-40 engineers | 3-5 engineers + AI agents |
| Cost | $8-12M | $500K-1.5M |
| Code Generation | 100% human-written | 80-90% AI-generated |
| Human Role | Write all code | Architecture, review, QA, edge cases |
| Iteration Speed | 2-week sprints | Daily/hourly iterations |
| Documentation | Often neglected | AI generates comprehensive docs |
| Test Coverage | Variable (60-80%) | High (90%+) - AI generates tests |

## AI Coding Agents Used

| Agent | Provider | Primary Use Cases | Strengths |
| --- | --- | --- | --- |
| Claude Code | Anthropic | Complex features, architecture, full files | Deep reasoning, large context, quality |
| Cursor (Claude/GPT) | Cursor AI | IDE integration, real-time coding | Fast iteration, codebase awareness |
| Aider | Open Source + Claude | Git-aware coding, refactoring | Multi-file edits, git integration |
| Gemini Code Assist | Google | Code completion, explanations | Speed, Google ecosystem |
| GitHub Copilot | GitHub/OpenAI | Inline completion, boilerplate | IDE integration, speed |
| Devin / OpenHands | Cognition / Open Source | Autonomous task completion | End-to-end feature development |

# Project Overview

## Development Model

| Attribute | Details |
| --- | --- |
| Total Duration | 4-6 months (16-24 weeks) |
| Phases | 8 phases (compressed from traditional plan) |
| Human Team | 3-5 engineers (Tech Lead, 2-3 Full-stack, 1 DevOps) |
| AI Agents | Claude Code, Cursor, Aider, Gemini, Copilot |
| Methodology | AI-driven sprints with daily human review |
| Code Review | All AI code reviewed by humans before merge |
| Testing | AI generates tests, humans verify coverage |
| Budget | $500K-1.5M (including AI API costs) |

## Human Team Responsibilities

| Role | Count | Responsibilities |
| --- | --- | --- |
| Tech Lead / Architect | 1 | Architecture decisions, AI prompt engineering, final code review, security |
| Senior Full-Stack Engineer | 1-2 | Complex integrations, AI output review, edge case handling, performance |
| Full-Stack Engineer | 1 | AI task delegation, code review, testing verification, documentation review |
| DevOps Engineer | 1 | Infrastructure, CI/CD, deployment, monitoring, security scanning |

## AI Agent Task Allocation

| Task Category | AI Responsibility | Human Responsibility |
| --- | --- | --- |
| Architecture Design | Generate options, document patterns | Make decisions, validate choices |
| Database Schema | Generate migrations, models, indexes | Review design, optimize queries |
| API Development | Generate endpoints, validation, docs | Review security, edge cases |
| Frontend Components | Generate React components, styles | Review UX, accessibility |
| Business Logic | Implement from specs | Verify correctness, edge cases |
| Testing | Generate unit, integration, e2e tests | Review coverage, add edge cases |
| Documentation | Generate API docs, guides, comments | Review accuracy, add context |
| Bug Fixes | Diagnose and fix from error logs | Verify fixes, prevent regression |
| Refactoring | Improve code quality, patterns | Approve changes, verify behavior |
| Security | Implement standard patterns | Security audit, penetration testing |

# Phase Summary

| Phase | Name | Duration | AI Agent Focus | Human Focus |
| --- | --- | --- | --- | --- |
| 1 | Foundation | 2-3 weeks | Scaffold, auth, DB schema | Architecture, security review |
| 2 | Core Platform | 3-4 weeks | Users, forms, datasets, expressions | Business logic review |
| 3 | Workflow Engine | 3-4 weeks | Designer, execution, tasks | State machine validation |
| 4 | Apps & Portal | 2-3 weeks | Low-code builder, portals | UX review, performance |
| 5 | Analytics | 2-3 weeks | Dashboards, reports, charts | Data accuracy, performance |
| 6 | Decision Tables | 1-2 weeks | Rule engine, evaluation | Logic validation |
| 7 | Integrations | 2-3 weeks | APIs, connectors, webhooks | Security, error handling |
| 8 | Launch Prep | 2-3 weeks | Testing, docs, optimization | QA, security audit, deployment |

## Daily Development Workflow

| Time | Activity | Participants |
| --- | --- | --- |
| 9:00 AM | Morning standup: Review AI output from overnight, prioritize tasks | Human team |
| 9:30 AM | Task delegation: Break features into AI-executable prompts | Tech Lead |
| 10:00 AM - 12:00 PM | AI coding session 1: Generate code with Cursor/Claude Code | Engineers + AI |
| 12:00 PM - 1:00 PM | Code review: Review morning AI output, provide feedback | Human team |
| 1:00 PM - 2:00 PM | Lunch + AI background tasks: Long-running generations | AI agents |
| 2:00 PM - 5:00 PM | AI coding session 2: Iterate based on review, new features | Engineers + AI |
| 5:00 PM - 6:00 PM | Integration: Merge approved code, run tests, deploy to staging | DevOps + AI |
| Overnight | AI background: Generate tests, docs, refactoring suggestions | AI agents |

# Phase 1: Foundation

Duration: 2-3 weeks | AI-Generated: ~90% | Human Review: ~10%

## 1.1 Objectives

- Scaffold complete project structure with Node.js, React, PostgreSQL

- Implement authentication (local + OAuth) and authorization (RBAC)

- Create database schema with multi-tenancy support

- Set up CI/CD pipeline and development infrastructure

- Establish coding standards and AI prompt templates

## 1.2 AI Agent Tasks

| Task | AI Agent | Prompt Strategy | Output |
| --- | --- | --- | --- |
| Project scaffold | Claude Code | "Create Node.js + React + PostgreSQL project with TypeScript, ESLint, Prettier, Docker" | Complete repo structure |
| Database schema | Claude Code | "Design multi-tenant schema for workflow platform with users, roles, permissions, audit" | Prisma schema + migrations |
| Auth system | Claude Code | "Implement JWT auth with refresh tokens, OAuth (Google, Microsoft), password reset" | Auth service + middleware |
| RBAC system | Claude Code | "Create role-based access control with permissions, role hierarchy, policy enforcement" | RBAC service + decorators |
| API framework | Cursor | "Set up Fastify with validation, error handling, rate limiting, OpenAPI docs" | API foundation |
| React setup | Cursor | "Create React 18 app with TypeScript, TailwindCSS, React Query, Zustand" | Frontend foundation |
| CI/CD pipeline | Claude Code | "Create GitHub Actions for test, lint, build, deploy to AWS/GCP with Terraform" | Complete pipeline |
| Docker setup | Copilot | "Dockerize all services with docker-compose for local dev" | Docker configuration |

## 1.3 Human Review Checklist

| Review Area | Criteria | Reviewer |
| --- | --- | --- |
| Architecture | Follows best practices, scalable, maintainable | Tech Lead |
| Security | No hardcoded secrets, proper auth flow, SQL injection prevention | Tech Lead |
| Database Design | Proper normalization, indexes, RLS policies | Senior Engineer |
| API Design | RESTful, consistent naming, proper status codes | Senior Engineer |
| Code Quality | TypeScript strict, no any types, proper error handling | All Engineers |
| Testing | Unit tests for critical paths, >80% coverage | All Engineers |

## 1.4 Sample AI Prompt

Prompt for Claude Code to generate the authentication system:

"Create a complete authentication system for a Node.js/Fastify application with the following requirements:

- JWT-based authentication with access tokens (15 min) and refresh tokens (7 days)

- Local authentication with email/password, bcrypt hashing, password strength validation

- OAuth 2.0 integration for Google and Microsoft with Passport.js

- Password reset flow with secure tokens and email notifications

- Multi-tenant support with account_id in JWT claims

- Rate limiting on auth endpoints (5 attempts per minute)

- Audit logging for all auth events

- TypeScript with strict mode, Prisma for database

- Include unit tests with Jest, >90% coverage

- Include OpenAPI documentation for all endpoints"

## 1.5 Exit Criteria

- All AI-generated code passes human review

- Authentication flow working end-to-end (signup, login, OAuth, password reset)

- RBAC enforcing permissions on all endpoints

- CI/CD pipeline deploying to staging automatically

- Test coverage >80% with all tests passing

- API documentation auto-generated and accessible

# Phase 2: Core Platform

Duration: 3-4 weeks | AI-Generated: ~85% | Human Review: ~15%

## 2.1 Objectives

- Complete account management (users, groups, roles, directory sync)

- Build drag-and-drop form builder with all field types

- Implement expression engine with formula parser

- Create dataset management with import/export

- Deliver SCIM 2.0 provisioning endpoints

## 2.2 AI Agent Task Breakdown

| Feature | AI Agent | Est. Time | Complexity |
| --- | --- | --- | --- |
| User CRUD + UI | Claude Code + Cursor | 2 days | Medium |
| Group management | Claude Code | 1 day | Medium |
| Directory sync (Azure AD) | Claude Code | 2 days | High |
| SCIM 2.0 endpoints | Claude Code | 2 days | High |
| Form builder backend | Claude Code | 2 days | High |
| Form builder UI (drag-drop) | Cursor + Claude | 3 days | High |
| Field types library (15+ types) | Claude Code | 2 days | Medium |
| Validation engine | Claude Code | 1 day | Medium |
| Conditional logic engine | Claude Code | 2 days | High |
| Expression parser (PEG.js) | Claude Code | 2 days | High |
| Expression functions (50+) | Claude Code | 2 days | Medium |
| Dataset CRUD + UI | Cursor + Claude | 2 days | Medium |
| Import/Export (CSV, Excel) | Claude Code | 1 day | Medium |
| Unit tests for all above | Claude Code | 3 days | Medium |

## 2.3 Form Builder AI Generation Strategy

| Component | Prompt Approach | Expected Output |
| --- | --- | --- |
| Field type registry | "Create extensible field type system with schema, renderer, validator for each type" | Plugin architecture + 15 field types |
| Drag-drop canvas | "Implement drag-drop form designer using dnd-kit with field palette, canvas, property panel" | Complete designer UI |
| Form renderer | "Create dynamic form renderer from JSON schema with validation, conditional logic" | Runtime form component |
| Expression parser | "Build PEG.js grammar for formula language supporting math, text, date, logic functions" | Parser + evaluator |

## 2.4 Human Focus Areas

| Area | Why Human Review Critical | Review Approach |
| --- | --- | --- |
| Expression Parser | Complex grammar, edge cases, security (injection) | Extensive test cases, fuzzing |
| SCIM Compliance | Must match RFC 7643/7644 exactly | Validate against SCIM test suite |
| Form Conditional Logic | Complex interdependencies, cycles | Logic verification, cycle detection |
| Data Import | Handle malformed data, encoding issues | Test with real-world messy data |
| Directory Sync | OAuth flows, token refresh, error handling | Test with actual Azure AD tenant |

## 2.5 Exit Criteria

- User management complete with all CRUD operations

- SCIM 2.0 passing compliance test suite

- Form builder creating forms with 15+ field types

- Expression engine evaluating 50+ functions correctly

- Datasets supporting import/export with error handling

- All features have >85% test coverage

# Phase 3: Workflow Engine

Duration: 3-4 weeks | AI-Generated: ~80% | Human Review: ~20%

## 3.1 Objectives

- Build visual workflow designer with BPMN-like notation

- Implement state machine execution engine

- Create task management with assignment rules

- Develop approval workflows with routing logic

- Build SLA monitoring and escalation system

## 3.2 AI Agent Task Breakdown

| Feature | AI Agent | Est. Time | Complexity |
| --- | --- | --- | --- |
| Workflow designer canvas | Cursor + Claude | 3 days | High |
| Node type library (10 types) | Claude Code | 2 days | Medium |
| Connection/edge handling | Claude Code | 1 day | Medium |
| Process definition schema | Claude Code | 1 day | Medium |
| State machine engine | Claude Code | 3 days | Very High |
| Token-based execution | Claude Code | 2 days | High |
| Parallel path handling | Claude Code | 2 days | High |
| Human task service | Claude Code | 2 days | Medium |
| Task inbox UI | Cursor | 2 days | Medium |
| Assignment rule engine | Claude Code | 2 days | High |
| Approval routing | Claude Code | 2 days | High |
| SLA monitoring service | Claude Code | 2 days | Medium |
| Escalation engine | Claude Code | 1 day | Medium |
| Kanban board UI | Cursor | 2 days | Medium |
| Integration tests | Claude Code | 3 days | Medium |

## 3.3 State Machine - Critical Human Review

The workflow execution engine is the most complex component. Human engineers must carefully review:

| Concern | Risk | Validation Approach |
| --- | --- | --- |
| State transitions | Invalid states, lost tokens | State transition diagram review, property-based testing |
| Parallel execution | Race conditions, deadlocks | Concurrent execution tests, lock analysis |
| Error handling | Stuck processes, data loss | Chaos testing, failure injection |
| Persistence | State not saved, recovery fails | Kill process tests, transaction verification |
| Performance | Slow at scale | Load testing with 10K+ concurrent instances |
| Idempotency | Duplicate execution | Replay tests, unique constraints |

## 3.4 Sample AI Prompt for Execution Engine

"Implement a workflow execution engine with the following requirements:

- Token-based execution model where tokens represent execution position

- Support node types: Start, End, Task, Approval, XOR Gateway, AND Gateway (split/join), Service, Timer

- Persist state to PostgreSQL with JSONB for flexibility

- Handle parallel paths with proper synchronization at join gateways

- Implement retry logic for service tasks with exponential backoff

- Use BullMQ for async task execution with job persistence

- Support process variables with scoping (global, local)

- Include comprehensive error handling with process-level error events

- Emit events for all state transitions for audit logging

- Ensure idempotent execution for crash recovery

- TypeScript with strict types, include state machine diagram in comments"

## 3.5 Exit Criteria

- Workflow designer creating valid process definitions

- Execution engine running linear, branching, and parallel workflows

- Task assignment working with all rule types

- Approval workflows routing correctly

- SLA monitoring triggering escalations

- Load test passing with 1000+ concurrent instances

# Phase 4: Apps & Portal

Duration: 2-3 weeks | AI-Generated: ~85% | Human Review: ~15%

## 4.1 AI Agent Task Breakdown

| Feature | AI Agent | Est. Time | Complexity |
| --- | --- | --- | --- |
| App builder shell | Claude Code | 1 day | Medium |
| Navigation builder | Cursor | 1 day | Medium |
| Page designer canvas | Cursor + Claude | 2 days | High |
| Component library (20+ components) | Claude Code | 3 days | Medium |
| Data binding system | Claude Code | 2 days | High |
| App publishing/versioning | Claude Code | 1 day | Medium |
| Portal site builder | Cursor | 2 days | Medium |
| Branding/theming system | Claude Code | 1 day | Medium |
| User registration flow | Claude Code | 1 day | Medium |
| External data connections | Claude Code | 2 days | High |
| Portal access control | Claude Code | 1 day | Medium |

## 4.2 Component Library Generation

AI generates complete React component library with single prompt:

| Component Category | Components Generated | AI Prompt Focus |
| --- | --- | --- |
| Data Display | Table, List, Card, Detail View, Tree | Data binding, sorting, filtering, pagination |
| Input | Form, Filter Bar, Search, Inline Edit | Validation, submission, controlled inputs |
| Charts | Bar, Line, Pie, Area, Gauge, KPI Card | Recharts integration, responsive sizing |
| Navigation | Tabs, Breadcrumb, Menu, Sidebar | Routing integration, active states |
| Layout | Grid, Stack, Split Panel, Modal, Drawer | Responsive breakpoints, nesting |
| Feedback | Alert, Toast, Progress, Skeleton | Accessibility, animations |

## 4.3 Exit Criteria

- App builder creating functional multi-page applications

- 20+ reusable components working with data binding

- Portal sites deployable with custom branding

- External data connections syncing correctly

- All components accessible (WCAG 2.1 AA)

# Phase 5: Analytics

Duration: 2-3 weeks | AI-Generated: ~85% | Human Review: ~15%

## 5.1 AI Agent Task Breakdown

| Feature | AI Agent | Est. Time | Complexity |
| --- | --- | --- | --- |
| Dashboard designer | Cursor + Claude | 2 days | High |
| Widget library (10 types) | Claude Code | 2 days | Medium |
| Chart components | Claude Code | 2 days | Medium |
| Query builder backend | Claude Code | 2 days | High |
| Report builder UI | Cursor | 2 days | Medium |
| Report scheduling | Claude Code | 1 day | Medium |
| Export (PDF, Excel) | Claude Code | 1 day | Medium |
| Process analytics | Claude Code | 2 days | Medium |
| Real-time updates (WebSocket) | Claude Code | 1 day | Medium |

## 5.2 Human Review Focus

| Area | Concern | Review Approach |
| --- | --- | --- |
| Query Performance | Slow queries on large datasets | EXPLAIN ANALYZE on generated queries |
| Data Accuracy | Incorrect aggregations | Verify calculations manually |
| SQL Injection | Dynamic query building risks | Security review, parameterization check |
| Memory Usage | Large report generation | Memory profiling, streaming |

## 5.3 Exit Criteria

- Dashboard designer with 10+ widget types

- Report builder with grouping, aggregation, filters

- Charts rendering accurately with drill-down

- Process analytics showing cycle time, SLA metrics

- Queries performing well on 1M+ row datasets

# Phase 6: Decision Tables & Datasets

Duration: 1-2 weeks | AI-Generated: ~90% | Human Review: ~10%

## 6.1 AI Agent Task Breakdown

| Feature | AI Agent | Est. Time | Complexity |
| --- | --- | --- | --- |
| Decision table editor UI | Cursor + Claude | 2 days | Medium |
| Rule evaluation engine | Claude Code | 2 days | High |
| Hit policy implementations | Claude Code | 1 day | Medium |
| Rule testing interface | Cursor | 1 day | Low |
| Dataset governance | Claude Code | 1 day | Medium |
| Row-level security | Claude Code | 1 day | Medium |
| Data quality rules | Claude Code | 1 day | Medium |

## 6.2 Exit Criteria

- Decision tables evaluating all hit policies correctly

- Rule evaluation performant (<10ms for typical tables)

- Dataset governance with audit trail

- Row-level security enforced consistently

# Phase 7: Integrations

Duration: 2-3 weeks | AI-Generated: ~85% | Human Review: ~15%

## 7.1 AI Agent Task Breakdown

| Feature | AI Agent | Est. Time | Complexity |
| --- | --- | --- | --- |
| REST API completion | Claude Code | 2 days | Medium |
| API documentation (OpenAPI) | Claude Code | 1 day | Low |
| Webhook system | Claude Code | 2 days | Medium |
| Connector framework | Claude Code | 2 days | High |
| Salesforce connector | Claude Code | 2 days | High |
| Google Workspace connector | Claude Code | 2 days | High |
| Microsoft 365 connector | Claude Code | 2 days | High |
| Slack connector | Claude Code | 1 day | Medium |
| Generic REST connector | Claude Code | 1 day | Medium |
| Integration builder UI | Cursor | 2 days | Medium |

## 7.2 Connector Generation Pattern

Each connector follows same pattern, enabling rapid AI generation:

| Connector Component | AI Prompt Template |
| --- | --- |
| Authentication | "Implement OAuth 2.0 flow for {service} with token refresh, secure storage" |
| Operations | "Create CRUD operations for {service} {objects} with pagination, filtering" |
| Field Mapping | "Generate type definitions and mappers for {service} to FlowForge schema" |
| Error Handling | "Implement retry logic, rate limit handling, error translation for {service}" |
| Tests | "Generate integration tests for {service} connector with mocked responses" |

## 7.3 Exit Criteria

- REST API 100% complete with OpenAPI documentation

- Webhooks delivering reliably with retry logic

- 6+ pre-built connectors working (Salesforce, Google, Microsoft, Slack, etc.)

- Integration builder creating custom connections

- All connectors have integration tests

# Phase 8: Launch Preparation

Duration: 2-3 weeks | AI-Generated: ~70% | Human Review: ~30%

## 8.1 Objectives

- Comprehensive testing (unit, integration, e2e, load, security)

- Performance optimization and caching

- Complete documentation (user, admin, API, developer)

- Security audit and penetration testing

- Production deployment and monitoring

## 8.2 AI Agent Tasks

| Task | AI Agent | Est. Time |
| --- | --- | --- |
| Generate missing unit tests to reach 90% coverage | Claude Code | 3 days |
| Generate e2e tests with Playwright | Claude Code | 2 days |
| Generate load tests with k6 | Claude Code | 1 day |
| Identify and fix performance bottlenecks | Claude Code | 2 days |
| Generate user documentation | Claude Code | 2 days |
| Generate API documentation examples | Claude Code | 1 day |
| Generate admin guide | Claude Code | 1 day |
| Implement security fixes from audit | Claude Code | 2 days |
| Generate runbooks for operations | Claude Code | 1 day |

## 8.3 Human-Led Activities

| Activity | Owner | Duration |
| --- | --- | --- |
| Security penetration testing | External firm + Tech Lead | 1 week |
| Performance testing analysis | DevOps + Senior Engineer | 3 days |
| Final code review sweep | All engineers | 2 days |
| Production environment setup | DevOps | 2 days |
| Monitoring and alerting configuration | DevOps | 1 day |
| User acceptance testing | Product + Engineers | 3 days |
| Documentation review and polish | Tech Lead | 2 days |
| Go-live checklist verification | All | 1 day |

## 8.4 Launch Checklist

- All tests passing (unit >90%, integration >85%, e2e critical paths)

- Load test passing (1000 concurrent users, <500ms p95 response time)

- Security audit passed with no critical/high findings

- Documentation complete and reviewed

- Monitoring dashboards operational

- Alerting configured for critical metrics

- Backup and disaster recovery tested

- Runbooks complete for common operations

# Budget Summary

## Cost Breakdown

| Category | Monthly Cost | 6-Month Total | Notes |
| --- | --- | --- | --- |
| Human Team (4 engineers) | $80,000-120,000 | $480,000-720,000 | Fully loaded cost |
| AI API Costs (Claude, GPT-4) | $5,000-15,000 | $30,000-90,000 | Heavy usage during dev |
| AI Coding Tools (Cursor, Copilot) | $500-1,000 | $3,000-6,000 | Per-seat licenses |
| Cloud Infrastructure (Dev/Staging) | $3,000-8,000 | $18,000-48,000 | AWS/GCP |
| Third-party Services | $1,000-2,000 | $6,000-12,000 | Auth0, SendGrid, etc. |
| Security Audit | - | $20,000-40,000 | One-time |
| Contingency (15%) | - | $83,000-137,000 | Buffer |
| Total | - | $640,000-1,053,000 |  |

## AI API Cost Estimation

| AI Usage Type | Est. Tokens/Day | Cost/Day | Monthly Cost |
| --- | --- | --- | --- |
| Claude Code (complex generation) | 500K-1M input, 200K output | $20-50 | $600-1,500 |
| Cursor (iterative coding) | 1M-2M input, 500K output | $30-80 | $900-2,400 |
| Code review/explanation | 200K input, 50K output | $5-15 | $150-450 |
| Documentation generation | 100K input, 200K output | $10-25 | $300-750 |
| Test generation | 300K input, 150K output | $10-30 | $300-900 |
| Total | 2-4M input, 1M output/day | $75-200 | $2,250-6,000 |

## ROI Comparison

| Metric | Traditional | AI Agent | Savings |
| --- | --- | --- | --- |
| Timeline | 18-24 months | 4-6 months | 12-18 months faster |
| Total Cost | $8-12M | $0.6-1.1M | $7-11M (85-90%) |
| Time to Market | Q4 2027 | Q3 2026 | 15+ months earlier |
| Team Size | 25-40 engineers | 4 engineers | 85% fewer people |
| Code Quality | Variable | Consistent (AI patterns) | More uniform |
| Documentation | Often incomplete | Comprehensive (AI-generated) | Better coverage |

# Risks and Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| AI generates buggy code | High | Medium | Mandatory human review, comprehensive tests |
| AI hallucinates incorrect patterns | Medium | High | Senior review, reference implementations |
| Complex features beyond AI capability | Medium | Medium | Human fallback, break into smaller tasks |
| AI API costs exceed budget | Low | Medium | Monitor usage, caching, use smaller models |
| Security vulnerabilities in AI code | Medium | High | Security audit, SAST tools, pen testing |
| AI context limits for large codebase | Medium | Medium | Modular architecture, focused prompts |
| Key human engineer leaves | Low | High | Document everything, cross-train, AI docs |
| AI service outages | Low | Medium | Multiple AI providers, local fallbacks |

## Quality Assurance Strategy

| QA Layer | Approach | Tools |
| --- | --- | --- |
| AI Output Review | Every AI-generated code block reviewed by human | PR reviews, pair programming |
| Automated Testing | AI generates tests, humans verify completeness | Jest, Playwright, k6 |
| Static Analysis | Automated code quality checks | ESLint, TypeScript strict, SonarQube |
| Security Scanning | Automated vulnerability detection | Snyk, OWASP ZAP, npm audit |
| Integration Testing | Test all module interactions | Testcontainers, docker-compose |
| Manual Testing | Human exploratory testing | Test plans, edge case hunting |
| Performance Testing | Load and stress testing | k6, Artillery |

# AI Agent Best Practices

## Effective Prompting Strategies

| Strategy | Description | Example |
| --- | --- | --- |
| Be Specific | Include all requirements, constraints, tech stack | "Using Fastify, Prisma, TypeScript strict..." |
| Provide Context | Share relevant existing code, schemas | "Given this schema: {...}, create..." |
| Request Tests | Always ask for tests with the code | "Include Jest unit tests with >90% coverage" |
| Specify Patterns | Reference design patterns to use | "Use repository pattern, dependency injection" |
| Include Examples | Show expected input/output | "Example: input {x:1} should return {y:2}" |
| Request Documentation | Ask for inline comments, JSDoc | "Include JSDoc comments for all public functions" |
| Break Down Tasks | Split complex features into smaller prompts | First schema, then service, then controller |
| Iterate | Refine output with follow-up prompts | "Good, now add error handling for..." |

## Code Review Checklist for AI Output

- Does the code actually solve the problem as specified?

- Are there any obvious bugs or logic errors?

- Is error handling comprehensive and appropriate?

- Are edge cases considered?

- Is the code secure (no injection, proper auth, etc.)?

- Does it follow our coding standards and patterns?

- Is the code efficient (no N+1 queries, proper indexes)?

- Are tests meaningful and covering critical paths?

- Is the code readable and maintainable?

- Are there any hardcoded values that should be configurable?

## When to Use Human Instead of AI

| Scenario | Reason | Approach |
| --- | --- | --- |
| Novel algorithms | AI may not have training data | Human designs, AI implements |
| Security-critical code | Too risky to trust AI alone | Human writes, AI reviews |
| Complex state machines | Subtle bugs hard to catch | Human designs states, AI implements |
| Performance-critical code | Requires deep optimization | Human optimizes, AI helps profile |
| Domain-specific logic | Requires business knowledge | Human specifies, AI implements |
| Debugging complex issues | Requires system understanding | Human debugs with AI assistance |

— End of Implementation Plan —